Operational Plan

Identifies the performance targets of individual business units and the way in which the targets will be achieved.

Discuss, clarify, confirm, monitor, review, reassess work expectations and requirements.

SMARTER Goals: Specific, Measureable - me, Achievable – challenging, Realistic & responsible, Timely, Empower & encourage, Review & reward

“What, when, where, how, who, evaluation.”

Team:

Strategic Purpose: Northern Corridor Partnership

Date: 30th September 2011

Review Date:

| Key Result Area/ Goals | Key Performance Indicators Quality, Quantity, Measurable | Strategies / Action | When By Specifics | By Whom Specifics |
| --- | --- | --- | --- | --- |
| - Bring together a key strategic group of stakeholders to address the issues identified by a due diligence of new residential and commercial-Industrial development occurring within the next 15 years between Noosa and Brisbane City | - The degree to which rapport is established with stakeholders - The quality of the Due Diligence completed - The number of stakeholders attending the forums. | - Complete a comprehensive due diligence around development from Noosa to Inner Brisbane - Select the key connectors who would be concerned with the information and invite to a forum. - Identify a champion/champions to fund the initiatives 1.4 Prepare a suitable presentation and send the invitation | May 2011 July 2011 July 2011 August 2011 | TM TM/GT GT/TM TM/GT |
| - Hold a successful forum to dissect the information contained in the presentation | - The quality of the discussion 2.1 The outcome of the meeting to identify another meeting date to continue discussions and to identify new influential members | 2.1 Prepare a sound process and presentation to stimulate discussion 2.2 Provide opportunity for open discussion 2.3 Encourage networking to occur 2.4 Request another meeting in 6 weeks. 2.4 Send comprehensive report | Mid August 2011 16th August 18th August 18th August 30th August | TM TM/GT TM/GT TM/GT TM |
| - Identify another date, agenda and place for forum 2 | The number of stakeholders who return The number of new stakeholders present | - Send invitation to all interested stakeholders - Source funding - Prepare an agenda 3.2 3.3 | 26th September | TM |
| - Hold the second forum | The number of stakeholders who attend | 4.1 see above 4.2 4.3 | 13th October | TM |
| - Ownership of the agenda by the group and a willingness to move ahead with their own agenda | The fact that there will be another meeting arranged by the stakeholders. | - Chair and lead the meeting to a successful conclusion, whatever the outcome might be - Send comprehensive report and recommendations to members 5.2 A third forum requested: PB to identify and engage speakers 5.3 | 13th October 1st November 15th November | TM TM TM |
| - Either nothing, or a further course of action identified by the group | The number of major partners willing to commit time and Knowledge to the partnership” ATC, NBN, Redcliffe Rail, Stockland. | 6.1 Plan another forum to deal with increased knowledge of the issues 6.2 Engage these 4 corporations to speak at next meeting 6.3 | 28th Nov 28th Nov | TM KM from DEEWR TM, Malcolm Paterson (RRL), Dane McCracken, (ATC), Ben Simpson, (Stockland), Rohan Anderson (NBN) |

# Development Plan

# Records the career & professional development goals of the individual.

# Identifies gaps in experience and skills

# Determines strategies and timelines to implement professional development.

# Name:

# Strategic Career Objective:

# Date:

# Review Date:

| Key Skill Area Goals (SMARTER) | Justification | Strategy ( How improvement will occur) | When By Specifics | By Whom Specifics |
| --- | --- | --- | --- | --- |
| 1. |  | 1.1 1.2 |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |