# DATA SET 3		 DOCUMENT ANALYSIS SCHOOL PLANNING AND IMPLEMENTATION RESOURCES

The purpose of this  ANALYSIS IS TO IDENTIFY DESIGN INTENTIONS  as a baseline against which IMPLEMENTATION and OUTCOMES  might be examined .

# It is  organised under the headings

# WHAT we found.:-                              					  Results/findings

# SO WHAT  have we learned from this experience ?;-                                       Key learnings

# NOW WHAT  we will do to inform our practice ? :-             Recommendations for “Next practice”

# WHAT we found.:-                              					  Results/findings

## Documents available to this review

# Documents not available to this review include

# Documented curriculum materials and teaching materials

# Completed PIMSIP referral forms

# Records of meetings of  PIMSIP  governance arrangements

## Implementation flowchart

PIMSIP has been delivered  in a context of  changing people , partners and purposes

## Espoused  Values, results , Implementation strategies and metrics of success

Aspirational goals are more likely to be couched in value laden terms such as

- “respond to the cultural, emotional physical and community needs of pacific island young people An increase in cultural identity within the school and wider community (Relate cdp program Overview )

- A greater understanding within the school community of Pacific Island and Maori young people and their specific needs ( NAB Schools First proposal )

- building students‟ confidence in their relationships with other cultures in Australia and abroad (2010 School Annual Report )

Strategies  are based on the hypothesis that

- increased engagement in class ,results in higher rates of attendance that leads to increased potential academic attainment  NAB Schools First proposal

- a layered response to the situation and a wrap around model that is embedded within the whole school community is preferred (NAB Schools First proposal

- The longer term  approach is to progress referred students  through the phases of Engage, Aspire ; Inspire ( Relate cdp strategic plan 2010)

Inputs and activities focus heavily  on community engagement  and the development of teacher awareness of cultural difference

- Community linkage – visitation program service agreement  (Service Agreement )

- Develop community mentoring network and training process  (Nab proposal )

- Strengthen teacher skills are an integral part of this program staff will receive skilling in cultural awareness, protocols and processes(Nab proposal )

Measures of success , when included, are more likely to be expressed in terms of  hard data on attendance , attainment and school disciplinary absences with little emphasis on recognition and reward for   the soft  social capital development espoused  in aspirational goals.

## Boundary partners/stakeholder groups

STUDENTS

2010

32  STUDENTS

2011

17 STUDENTS  continue with PIMSIP

18 STUDENTS not previously engaged participate in VAL  active volunteering program

2010

20 STUDENTS

2011

9 STUDENTS  continue with PIMSIP

???

2010

35 STUDENTS

2011

11STUDENTS continue with PIMSIP

60 students not previously referred engaging

6

4                                                        6

Of the 87 students who participated in PIMSIP 2010 ,36  were referred  again in 2011 ( 41 %)

Some  34  FACTORS  influencing student performance were identified in the student referral form.

The NAB  proposal identifies the  intention for VAL students to   become the mentors and work with younger peers within the school community

PARENTS

The NAB proposal indicates a genuine willingness to work in partnership with Pacific Island and Maori parents and communities - an identified best practice  cited by the Pacific Island Framework for Action in Education. There is an anticipated increase the involvement of parents in the life of the school community .

COMMUNITY

A semantic map of the NAB proposal identifies 50  uses of the word community in comparison with 2 of the word teacher  Many of these focus on the role of “the community partner “  & “ community mentors “ as  representatives of the school  PI community.

The community partner  was  engaged in 2010 and  again in 2011 on the strengths of the 2010 School Annual report “ A partnership between Forest Lake SHS and Relate Community Development Program (CDP) specifically addressed identified needs of students of Pacifika and Maori cultural heritage. The positive outcomes of this partnership were used as the platform for a successful National Bank of Australia Schools‟ First Application (valued at $25000).

The Service agreement  identifies an agreement  for the community partner to establish a Community linkage – visitation program

DESIGNERS

The role  is not specifically mentioned in the documents examined . The function has been performed by  one of the school guidance officers who , with team support was successful in securing the NAB Schools first  seed funding of $25K

TEACHERS

The NAB Schools First Funding Application  defines the following  focus for teacher engagement

- Cultural awareness progressions   by providing appropriate cultural training to increase teachers’ understanding of Pacific Island and Maori culture, structure and family system, as well as preferred learning styles.

A  word cloud generator of the 25 most commonly used works  in the NAB Schools First Funding Application

The service agreement  does not mention  any role for class  teachers  in the delivery of  PIMSIP

Relate cdp Program overview  also fails to identify a specific role for class teachers who refer students  to PIMSIP

ADMINISTRATION

Program governance structures for  2011 focussed on regular meetings  for

strategic team: comprised of, principal, guidance officer, and community partner

- develop and design the strategic and operational plan

- to meet monthly

- to finance and audit budget of the program

- to manage and review program delivery

- analyse the broader implications of the strategic plan

school management team:  comprised of the strategic team and deputy principal, middle school management and community development officer

- support delivery of the program

- communicate intent of program to the school community and wider community

- manage the referral process

- manage the reactive aspects of the strategic plan

- celebrate success of the program

- develop community links and negotiate community networks

case management of team: comprised of community partner facilitator, teachers, guidance officer, mentors community develop project development officer

meet weekly

manage daily issues of student well being

facilitate family group conferencing, family and community visitation

interagency referral process

facilitating interface between class teacher and student’s family

:

# SO WHAT  have we learned from this experience ?;-                                       Key learnings

# Do we pursue Documents not available to this review include ??

# Documented curriculum materials and teaching materials

# Completed PIMSIP referral forms

# Records of meetings of  PIMSIP  governance arrangements

# I’m sure this information is in your collective heads so could we just provide informally /anecdotally

# Congruence  of  intent within and across documents is  difficult to track.. Different authors composed  documents in response to  different frameworks and applied different language to the design, implementation and review phases of PIMSIP

The function  of program design has been performed by  one of the school guidance officers who , with team support was successful in securing the NAB Schools first  seed funding of $25K

While the  admin team engaged in the program design and monitoring remained relatively constant , there were considerable changes in the role each played ( ie principal leave necessitated a number of internal  leadership team changes )

# NOW WHAT  we will do to inform our practice ? :-             Recommendations for “Next practice”

| CHILD FACTORS | FAMILY FACTORS | SCHOOL CONTEXT | COMMUNITY & CULTURAL FACTORS, LIFE EVENTS |
| --- | --- | --- | --- |
| 1. Child mental health issues | 10. Parental mental health issues | 21. School failure | 27. Socioeconomic disadvantage |
| 2. Early initiation of violence and delinquency | 11. Parental substance abuse | 22. Deviant peer group | 28. Population density and housing conditions |
| 3. Substance abuse | 12. Criminality | 23. Victim of bullying | 29. Neighbourhood violence and crime |
| 4. Hyperactivity / disruptive behaviour | 13. Experiencing family violence | 24. Peer rejection | 30. Violence acceptable as a response to frustration. |
| 5. Low self-esteem | 14. Relationship discord | 25. Truancy | 31. Lack of support services |
| 6. Early involvement in sexual behaviour | 15. Negative interactions / social isolation | 26. Early and persistent antisocial behaviour at school | 32. Social or cultural discrimination |
| 7. History of physical, sexual emotional abuse or neglect | 16. Long term unemployment |  | 33. Divorce and family break up |
| 8. Lack of vocational skills and job | 17. Homelessness or lack of stable accommodation. |  | 34. Death of a family member |
| 9. Grief and loss / attachment issues | 18. Running away from home |  |  |
|  | 19. Parenting skills |  |  |
|  | 20. Stress Management |  |  |