## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 2/2/2012 - 2/8/2012
Group Member | Role | Progress Description | Time Alloted (hrs)
Matthew Rasler | Project Manager | Group Meeting Preperation | 2 hours
|  | Group Meeting (presentation construction and preperation) | 4 hours
| Team Member | Progress reporting | 1/4 hour
| Web Application Programmer | Web site design | 2 hours
|  | Refined HTTP code for QT | 1 hour
Andrew Habegger | Software Developer | Fixed a bug involving byte communication protocol | 1 hour
|  | Created an ASCII communication protocol | 3 hours
| Team Member | Progress reporting | 1/4 hour
|  | Group Meeting (presentation construction and preperation) | 4 hours
Eun Young Shin | Cmap Manager | Modified and Updated Group Cmap | 3 hours
| Team Member | Group Meeting (presentation construction and preperation) | 4 hours
|  | Progress Reporting | 1/4 hour
| Student | Prepare Presentation | 2 hours
|  | PMBOK Summarize Ch.7 | 2 hours
Mark Parker | Software Developer | Installation of PHP IDEs | 3 hours
|  | PHP code modules (db test, HTTP Post->SQL module) | 3.5 hours
| Software Developer/Tester | PHP code installation, PHP-database interaction | 1 hour
| Team Member | Presentation preparation | 2 hours
|  | Progress reporting | 0.25 hours
| Student | PMBOK KA 6 | 1 hour
Notes from Group Meeting 2/8/2012
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date