## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 1/25/2012 - 2/1/2012
Group Member | Role | Progress Description | Time Alloted (hrs)
Matthew Rasler | Project Manager | Group Meeting Preperation | 3 hours
| Web Interface Programmer | Designed GUI Application (in QT) to verify software capability of application to web communication. | 10 hours
|  | Developed Psuedo-code to assist Mark in PHP development | 1 hour
|  | Set up database and server access, communicated instructions for use, to enable Mark to develop PHP component for Web Service. | 1 hour
| Student | PMBOK 2-3 | 2 hours
Andrew Habegger | Assistant Project Manager | Group Meeting Preperation | 1 hours
| Software Developer | Modified firmware to use SETOUT instead of UART (propagation delay reduced from 5s to 0.5s) | 2 hours
| Hardware Developer | Engineered RS-232 TX to RS-485 TX cable | 1 hour
| Student | PMBOK 2-3 | 2 hours
Eun Young Shin | Group Member | Modifiying Group Cmap | 3 hours
| Student | Read PMBOK 2-3 | 4 hours
|  | Summarize PMBOK 2-3 | 2 hours
Sunyoung Park | Group Member | Read PMBOK chapter5-6 | 2 hours
| Student | Summarize PMBOK chapter5-6 | 2 hours
|  | Learning Orchard CMS | 3 hours
Mark Parker | Programmer | Researching PHP and QT, HTTP POST | 4 hours
| Student | Wrangling with help desk for access to student account | 4 hours
| Group Member | Group Meeting and presentation prep | 3 hours
Notes from Group Meeting 2/1/2012
Group All:
Confirm and Coordinate all Group Members Progress on personal CMAPs including PMBOK 1-3. Accomplished
Collect and upload progress report for this week (this). Accomplished
Matthew:
Confirm access and privelages on group CMAP for all members. Accomplished
Iterate through Prof. Tanik's announcements to insure on task. Accomplished.
Presentation discussion and preperation.
Schedule Friday meeting.
Mark:
Discuss progress on setting up server and database. Assist as needed. Accomplished
Discuss QT Communication Device and operation thereof. Accomplished
Eun Young:
CMAP access. Accomplished
CMAP progress discussion. Accomplished
Sunyoung:
Webpage progress discussion. Accomplished
Andrew:
Setup video for presentation. Accomplished.
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler | Complete Project Preperation
Direct in Server Side Application
Refine HTTP code for QT
Mark Parker | Complete Project Preperation
Have database and server working
Understand Dreamweaver server access
Andrew Habegger | Complete Project Preperation
Continue Refining Primary Application
Eun Young Shin | Complete Project Preperation
Complete CMAP revitilization
Sunyoung Park | Complete Project Preperation
Have front page of group web page completed