## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status: 1/18/2012 - 1/24/2012
Group Member | Role | Progress Description | Time Alloted (hrs)
Matthew Rasler | Project Manager | Group Meeting | 2 hours
|  | Designed and implemented weekly progress reporting communication tool | 1 hour
| Web Development Team Lead | Researched and implemented communication mechanism to communicate securely from primary application to web application | 6 hours
Sunyoung Park | Group Member | Download Cmap | 1hr
|  | PMBok | 1hr
|  | BaseCamp | 1hr
|  | PMBok Chapter4 | 1hr
|  | Download Visual | 1hr
|  | Download Msproject | 1hr
|  | Download Visio | 1hr
Mark Parker | Design Engineer | Review SRS, Architecture for updates. | 1hr
|  | PMBOK KAs 2-5 | 3 hr
Andrew Habegger | Software Developer | Debugged serial communication issues, implemented jam detection algorithm, refined user interface | 6 hr
|  | PMBOK KAs 1-2 | 1.5 hr
Eun Young Shin | Group Member | Complete Student Evaluation | 1hr
|  | Setup Cmap, Basecamp | 3hrs
|  | Setup Acclaro | 1hr
|  | Setup Visio, MS Project, Visual Studio | 2hrs
|  | Read & Summarize Chapter4 | 4hrs
TASKS FOR THIS SEMESTER:
-Primary Application: Software
--Refine Jam Detection Logic. We've abandoned RANSAC and are now going with an algorithm supplied by the client.(2/1/12)
--The GUI needs refined.(2/1/12)
---Configuration tab radio buttons need replaced with stylized list view.(2/1/12)
---QTimer needs replaced with event-driven signals/slots. Polling is making the GUI lag. (2/1/12)
--Needs to serialize egg counts.(2/1/12)
--Refine Logging. Add error descriptions for serial communication (e.g. Time outs; bad responses (too little, too much); application start time, application end time (for opening and closing the app))
--Hamming codes to detect/correct communication errors.
-Primary Application: Firmware
--Write pbasic program to use dedicated serout/serin pins to bypass UART.
--Hamming code receiving/transmission
-Hardware
--Ruled out 422 line. Using 485.
--Test 486 through a dedicated serout and serin pin to bypass the UART.
--Install ADAM serial converters.
-web Development 1: Business Site
--To be developed further.
--Matt and Mark researching application-to-web page connectivity.
-Web Development 2: Group Site
--This will be a web version of our CMap, but more visually appealing.
--Incorporates a Content Management Solution (CMS): Orchard.
TASKS FOR THIS WEEK:
-Eun Young
--Update the group cmap. It needs to be more streamlined.(2/1/12)
---Make each RUP Phase a separate CMap.(2/1/12)
-Matt
--Give Sunyoung cmap stuff.(1/25/12)
--Email Eun Young web access (group cmap). (1/25/12)
--Get familiar with HTTP Posts from Qt. (2/1/12)
-Sunyoung
-will research the Orchard Content Mangement System.(2/1/12)
-Create an initial version of the group website with Orchard.(2/1/12)
-Mark
--Send these notes to Prof. Tanik.(1/25/12)
--Get familiar with Qt and HTTP Posts.(2/1/12)
--Learn PHP basics.(2/1/12)
-Andrew
--Refine Jam Detection Logic, using algorithm supplied by the client.(2/1/12)
--Refine The GUI.
---Configuration tab radio buttons need replaced with stylized list view.(2/1/12)
---QTimer needs replaced with event-driven signals/slots. Polling is making the GUI lag.(2/1/12)
--Implement serialized egg counts.(2/1/12).