## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 2/15/2012 - 2/22/2012
Group Member | Role | Progress Description | Time Alloted (hrs)
Matthew Rasler | Web Developer | Created initial working web page, with active components, extensible. | 13
| Web Developer | Formilized concepts previously discussed with Mark, database structures and elements | 1
| Group Member | PMBOK 4,5,6 | 2
| Project Manager | Group Meeting preperation, slide show prep | 2
Sunyoung Park | Group Member | PMBOK 4,5,6 | 2
|  | Management Web Page | 1
|  | Installed QtSDK and Reviewed Sample Codes | 1
Eun Young Shin | Group Member | PMBOK 4,5,6 | 2
|  | Management Cmap | 1
|  | Installed QtSDK and Reviewed Sample Codes | 1
Mark Parker | Web Developer / Database Developer | Met with Matthew, reviewed his requirements for format of storing data and revised the initial database structure. Expanded and described items using Access. | 2
| Group member | Developed slide(s) regarding database structure and tradeoffs. | 1
Andrew Habegger | Software Development | Coding Earl Software Updates, deciphering Hamming Algorithm approach | 7
| Group Member | Presentation Preperation, Slide compilation for group | 2
|  | PMBOK 4,5,6 | 2
Notes from Group Meeting 2/22/2012
Attached to Basecamp, to do list; add here.
Todo list:
Complete table structure and variables defined to be sent to database and web application
Design mockup web application
Gantt chart weekly progress
Write NetworkAccessManager Class
Application Architecture V4.0
Sql queries discussed
Weekly CMAP backup at group meeting SOP and FMEA update
PMBOK 1-6 completed
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler | Write NetworkAccessManager Class
Design mockup for website complete
FMEA update
Andrew Habegger | Hamming algorithm employed in EARL
Clickable buttons in EARL for persistant disable/enable
Mark Parker | Create Database structure for WEbEARl
Variables defined for passing
Eun young Shin | Read SRS from last semester, understand FR-DP concepts
Learn axiomatic design concepts
Sunyoung Park | Read SRS from last semester, understand FR-DP concepts
Learn axiomatic design concepts