## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 3/14/2012 - 3/21/2012
Group Member | Role | Progress Description | Time Alloted (hrs)
Matthew Rasler
Mark Parker | Student | Exam Study | 5 hours
| Web Designer | Framework for product website | 6 hours
Eun Young Shin | Student | Preparing Exam | 10 hour
|  | Weekly Progress | 0.2 hour
|  | PMBOK KA8 | 2 hour
|  | Convert DM to Excel | 1 hour
Sunyoung Park | Student | Preparing Exam | 10 hour
|  | Weekly Progress | 0.2 hour
| Team Member | Gantt Chart | 1 hour
Andrew Habegger | Student | PMBOK KA8 | 1 hour
| Software Developer | Created resources files for product website | 4 hours
Mark Parker | Class Liaison | Exam 1 Review Sheet | 9 hours
| Design Engineer | SRS and FR review | 2 hours
|  | Convert DM to Excel | 1 hour
Notes from Group Meeting 3/21/2012
Starting new phase with high priority: develop web front for EARL sales front.
Identify layout, branding, merchandising parameters.
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler | Continue working on product website, finish framework, start implementation
Consider cart functionality and approach
Andrew Habegger | PMBOK KA 9
Build prototype merchant website.
Mark Parker | PMBOK 8-9
Update SRS, FR/DP, FMEA, SDD
Eun Young Shin | Convert files on cmap to readily accesible files
Sunyoung Park | Update group webpage