## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 3/28/2012-4/4/2012
Group Member | Role | Progress Description | Time Alloted (hrs) |  | PM Grade | Self Grade | Explanation Needed
Matthew Rasler | Project Manager | New Communication Template for Progress Reporting | 1
| Web Developer | Added content to Business and Products Pages | 5
|  | Documented and Sent out Request for Information from Client | 1
| Group Member | PMBOK Kas Finalized | 2
|  | Total: | 9 |  | 10 | 10
Eun Young Shin | Assistant Design Engineer | UML Training Session/Class Diagrams | 1.5
| Group Member | Converting Gantt Chart | 0.5
| Group Member | Preparing Presentation | 3
| Cmap Manager | Update Cmap | 1.5
| Group Member | PMBOK Kas Finalized | 2
|  | Total: | 8.5 |  | 10 | 10
Sunyoung Park
|  | Total: | 0 |  | 7 | 7
Andrew Habegger
|  | Fixed detection bug | 3
|  | PMBOK Kas Finalized | 2
|  | Total: | 5 |  | 10 | 10
Mark Parker | Design Engineer | DM | 3
|  | DSM | 6
|  | FR-DP | 2
|  | SRS | 2
|  | Format conversions via Photoshop | 4
|  | UML Class Diagrams | 2
|  | UML Use Case Diagrams | 1
| Classroom Liaison | UML Training Session/Research | 2
| Group Member | PMBOK KA 8 | 1
|  | PMBOK KA 9 | 1
|  | Total: | 24 |  | 10 | 10
Notes from Group Meeting 4/4/2012
New Test posted
Finalize SWEBOK and PMBOK due today
MARK, EUN YOUNG, SUNYOUNG-> UML discussion
Use case diagram
New Progress reporting and communication rules
Outlined expectations
Scheduled visit to farm for photography-> SUNDAY 15
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler | Continue work on web page
Andrew Habegger | Communicate with sponser and fill out request for information sheet for webcontent
By weekend
Mark Parker | Finalize Class Diagrams and develop Component Diagrams
Updating SRS with revised FRs
Updating FR list-> reiterating through axiomatic process
Eun Young Shin | Convert and upload new axiomatic files to cmap
SWEBOK finalize
Work with Mark to finalize axiomatic files and SRS
Review Use Case Diagrams and methodology
Finalize Class Diagrams and develop Component Diagrams
Sunyoung Park | SWEBOK finalize
Consider task of exporting web page for final binder
Continue working on .div structure for business web page