## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 4/11/2012 - 4/18/2012
Group Member | Role | Progress Description | Time Alloted (hrs) |  | PM Grade | Self Grade | Explanation Needed
Matthew Rasler | Web Designer | Photograph EARL and farm | 3
| Web Developer | Debugged Validation form for email | 2
|  | Finished solicitation of web information | 2
|  | Determined Commerce solution archetecture | 3
|  | Total: | 10 |  | 10 | 10
Eun Young Shin | Group Member | Exam1 Redo | 3
|  | Exam2 | 3
| Documentation | Update PMP | 2
|  | Total: | 8 |  | 10 | 10
Sunyoung Park | Group Member | Exam1 Redo | 3
|  | Exam2 | 3
| Group web page | Update resources | 2
|  | Total: | 8 |  | 10 | 10
Andrew Habegger | Software Developer | Debugged several program issues | 4
|  | Total: | 4 |  | 10 | 10
Mark Parker | Design Engineer | SDD Refurb | 3
|  | Component Diagram | 2
|  | Use Case Diagram | 2
|  | Modified SRS with new Axiomatic Components | 4
|  | Total: | 11 |  | 10 | 10
Notes from Group Meeting 4/18/2012
Individual group member status
progress reports
email sponsor
last week finalization of forms
everyone printout progress reports, exam I, exam ii
assign new portfolio
cmap finalization and print
web page finalization and export
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler
Create new splash pages with pictures
start to develop commerce solution for sales
finish content in web pages
Andrew Habegger | Fix bug caused by dynamic thresholds
Fix bug caused by excessive idling
Mark Parker | Build new portfolio with modified componenents
Finish SDD
Eun Young Shin | Finalize cmap, export, and print
Organize content for portfolio and start printing
Sunyoung Park | finalize group web page, export, and print
Organize content for portfolio and start printing